## tasks-sheet
Tasks | Date | Assigned To | Status | Remarks
Update Sheets with String Matching Data on 1L profiles - Case Insensitive & single character handling | 2021-02-25 | Shubham | Done | Ran on 10k profiles, hardware issue
Filter profiles for manual tagging & manually tag the profiles | 2021-02-26 | Shubham | Done | Kindly Check the sheet with "Actual" Column Name
Get the scores define on Metric Sheet for manually tagged profiles | 2021-02-26 | Shubham | Done
Run NER & get the similar metrics on them | 2021-02-26 | Shubham | Done | Ran NER with 70 threshold
Prepare the Training Data and prvide to Data ops team | 2021-03-08 | Shubham | Done | Given to Simnachal and Team
NER (sm model used) | 2021-03-08 | Shubham | Done | Got 1 matching entry in 100
NER(used sm, md lg) and comparison with and without fuzzymatch on 100 entries(Train Data) | 2021-03-09 | Shubham | Done | Bad performance of NER due to lowercased summary
NER resolving issue of why we are not getting tagged entries in string; working on casing issue; | 2021-03-10 | Shubham | Done | truecase significantly improved NER performance as of now
Major summary entries are completely lowercased which reduces NER accuracy drastically
Get the Data Properly Tagged by Simanchal |  | Rishi
Get count of Tech row wise and compare with Truecase and without truecase | 2021-03-11 | Shubham | Done | With Truecase:34 Technologies is Count; Without Truecase: Count is 2
Look for Adding own Vocabulary option in truecase if possible |  | Shubham | Done | Instead look for spacy NER
Go through this paper and see if any experiment we can run on the data that we they have. | 2021-03-12 | Shubham
Try to incorporate more tags in the NER | 2021-03-12 | Shubham | Done | Technology Count Matched increased to 52 from 34 now. This is after including other tags than ORG in our list
Can we add our vocabulary into Spacy NER training set? | 2021-03-12 | Shubham | Done | Yes, we can add our custom vocab: https://spacy.io/usage/rule-based-matching#entityruler
Try CoreNLP | 2021-03-12 | Shubham
Try : https://huggingface.co/ | 2021-03-12 | Shubham | Done | Yes, More Company Names are getting tagged
Try : https://cloud.google.com/natural-language | 2021-03-12 | Shubham
string match(non-dictionary words) + spacy NER (dictionary words) | 2021-05-11 | Shubham | Done | Now, try to catch Contextual cases like greenhouse where the name is common with general english and being a technology name
DAILY TASK SHEET UPDATE (w.e.f 12 May 2021)
Find out Approaches for NER for contextual greenhouse like cases/Roadmap with training data | 2021-05-12 | Shubham

## tracker_mohit_task
Tasks | Date | Assigned To | Status | Remarks
NER,Spacy, Truecasing, Huggingface, POS basics | 2021-12-05 | Mohit | Done
Blog - https://nanonets.com/blog/named-entity-recognition-2020-guide/ | 13/05/21 | Mohit | Done
Explore New NLP Approcahes (Lim 1- Company names matched with Nouns, Lim 2- DataSize) | 13/05/21 | Mohit | Halted
Dashboard Exploration | 14/05/21 | Mohit | Done
Spacy for NER | 18/05/21 | Mohit | Halted
String matching - Tech words | 20/05/21 | Mohit | Done | https://drive.google.com/file/d/1-s7AXtq0kP1XyGVZOUww-Cln4Ynd2oXi/view?usp=sharing
BERT understanding | 25/05/21 | Mohit | Done